VOLUME 2

SECTION 3

SPECIAL CONDITIONS

# CONTENTS

# These conditions amplify and supplement the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, the General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the General Conditions. Other Special Conditions should be indicated afterwards.

Article 2	Language of the Contract

2.1	The language used shall be English or Croatian.

Croatian shall be used when dealing with project design plans, drawings, works register, invoices etc.

Article 3:	Order of precedence of contract documents

The following documents will be deemed to form and be read and construed as part of this Contract, in the following order of precedence

(a) the Contract

(b) the Special Conditions

(c) the General Conditions

(d) the Technical Specifications

(e)  the Bill of Quantities and Price Schedule, possibly after arithmetical corrections

(f) the tender with the appendix

(g) any other document forming part of the Contract

Addenda have the order of precedence of the document they are modifying.

In the event of any ambiguity or divergence between these documents, their provisions shall be applied according to the above order of precedence.

Article 4	Communication

4.1	Contact person for the Contracting Authority will be: Ljerka Vučković, City of Belišće, Kralja Tomislava 206, Belišće, Tel. 031/400-636, Fax 031/400-602, e-mail: ljerka.vuckovic@belisce.net

Contact person for the Contractor will be:

Article 5	Supervisor and Supervisor’s representative

5.1	The Supervisor shall carry out the duties specified in the contract signed between the Contracting Authority and the selected Supervisor which follows the national legislation regarding civil construction and supervision and the Rulebook on supervision issued by the Chamber of civil engineers.

Article 8	Documents to be provided

8.1	Contracting Authority will provide the Contractor and the Supervisor with following documents: prepared Execution design drawings and plans necessary for implementation of tasks, Bill of quantity, Technical specifications and other contract documents.

Article 15	Performance guarantee

15.1	The amount of the performance guarantee will be 10% of the amount of the Contract and any addenda thereto.

Article 17	Programme of implementation of tasks

17.1	The Contractor is obliged to submit the Programme of implementation of tasks to the Supervisor for approval within maximum 15 days from the date of Contract signature. The Programme of implementation of tasks shall be drawn up in accordance with the 17.1 of the General Conditions.

Article 19	Contractor’s drawings and execution studies

19.7	The language of the manuals and drawings will be Croatian or English.

Article 20	Sufficiency of tender prices

20.3	Since the Contractor is deemed to have determined its prices on the basis of its own calculations, operations and estimates, it shall carry out without additional charge any work which is the subject of any item whatsoever in its tender for which it indicated a unit price according to the Article 20. of General Conditions.

Article 24	Interference with traffic

24.1	Any permission regarding traffic regulations will be procured by the Contractor in accordance with national laws.

Article 34	Period of implementation of tasks

34.1	The Contractor will execute the contracted works within 4 (four) months, starting with the date of introduction to the building site.

Article 36	Delays in the implementation of tasks

36.1	The rate of liquidated damages for delays in the completion of works shall be 0.2% of the contract price for every day or part thereof which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 5 % of the contract price.

Article 40	Origin and quality of works and materials

40.1	All goods purchased under the Contract must originate in any eligible source country as defined in IPA CBC HU-HR 2007-2013 Programme. For these purposes, ‘origin’ means the place where the goods are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods must be determined according to the EU Customs Code or the applicable international agreement.

Article 41	Inspection and testing

41.2 	Inspection and testing shall be performed in accordance with the requirements of the applicable Croatian technical regulations and legislation as well as all related designs.

Article 44:	General principles for payments

44.1	Payments shall be made in national currency HRK or in Euro, in accordance with the issued interim invoices.

Article 46	Pre-financing

46.1	No pre-financing is foreseen within this Contract.

Article 47	Retention monies

47.2.	The retention sums shall be substituted by a retention guarantee. The tenderer must provide a retention guarantee in the amount of 5% of the contract value and in the form set out in the tender dossier (Volume 2, Section 4). It must meet the essential requirements set out therein. It must be provided in the form of a bank guarantee. The bank guarantee for the purpose of warranty period (retention guaranty) shall be delivered by the Contractor together with the final invoice, before final acceptance of the works.

Article 49	Measurement

(*)	This is a unit-price contract.

Article 50	Interim payments

50.1	Interim payment shall be made according to interim invoices and according to the agreed work plan.

Article 51	Final statement of account

51.1	The Contractor shall submit to the Supervisor a draft final statement of account when it applies for the provisional acceptance certificate. In order to enable the Supervisor to prepare the final statement of account, the draft final statement of account is submitted with supporting documents showing in detail the value of the work done in accordance with the contract.

51.2	Within 30 days from issuing the certificate of final acceptance referred to in article 62, the Supervisor shall prepare and sign the final statement of account.

Article 61	Defects liability

61.1	The defects liability period is defined as the period commencing on the date of provisional acceptance, during which the Contractor is required to make good any effect in, or damage to, any part of the work which may appear or occur during this period as notify by the Supervisor or the Contracting Authority. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the General Conditions.

61.7	The defect liability period will be 24 months (2 years) starting from the day of issuing the provisional acceptance.

Article 68	Dispute settlement

68.4	Any dispute arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of the Municipal Court in Valpovo applying the national legislation of the Contracting Authority which is the Republic of Croatia.